FPH Special Interest Group - Sustainable Development Workplan

January 2018 Update – Paper C

- Key committee contacts

| Name of SIG: | Sustainable Development |  |  |
| --- | --- | --- | --- |
| Chair: Contact details: | Jeremy Wight |  |  |
|  | Email: jeremywight73@gmail.com |  | Phone number: 07803 507079 |
| Deputy chair: Contact details: | Helen Ross |  |  |
|  | Email: hzross2@myphone.coop |  | Phone number: 07890 397924 |
| Is your SIG a parent for any sub-cSIGs? If so, which sub-cSIGdo you provide formal oversight for? | SIG name | SIG chair |  |
|  | - Food Sub Group | Amanda Donnelly |  |
|  | 2. |  |  |

| Objective / activity | Please list any key milestones or deadlines | What impact do you expect these activities will have? | How will you measure the impact / success of these activities? | 29 January 2018 |
| --- | --- | --- | --- | --- |
| - Produce publications e.g. factsheets, booklets or webpages that explain the relationship between climate change and health and the role of Public Health practitioners in tackling climate change and the causes of climate change. Who from the SIG is leading on this activity? Jenny Griffiths | - Initial drafts of suite of publications by December 2017. - Consultation with interested parties completed by end February 2018 - Publication by end March 2018 Milestone updated 29 January – aim to complete 16 documents by October 2018. | To support PH practitioners in making the case for the links between climate change and health. Increased influence of climate change and environmental sustainability considerations in public health policies. Resources available to support PH trainees in acquiring the relevant competencies. The outcome will help to inform those well-established Consultants in PH who are not aware of the importance of Sustainable Development and its relevance to Public Health. | By monitoring the use of the resources – number of downloads from the website, etc. Informal monitoring of the prevalence of climate change and environmental considerations in policy and strategy documents, DPH annual reports, etc. Survey of FPH members?? | People willing to volunteer their time and expertise to work with JG on this – Helen Ross, Paul Southon, Sue Atkinson & Emily. HR fed this back to JG via minutes and catch up calls. JG has started work on the 16 FPH SD SIG package development. It is envisaged that this will be placed on the new FPH website when available (probably by May). Emily liaised with the Registrars network over volunteer Registrars to assist and 6 initially expressed an interest. So far Alice Munro has kindly agreed - to undertake literature reviews and write; - Knowledge – Health and the Natural Environment - Skills – Commissioning - Fuel poverty if time Others to confirm their offers by 2 February to Jenny. Emily will prompt them for a response and will send details of additional offers to Jenny. Guidance is included in the scoping document (circulated to SIG members 29 January). GB reported in advance of the meeting that it is not possible for the SIG to access the PHE e learning package on sustainability. Update welcome from JJ – re sharing the package from the Ambassador Place leads full days training with DP and SD colleagues? Update welcome from SS re Health knowledge – Faculty developing e learning approaches. We could develop one for the FPH on SD. |
| - Support specialty registrars and other practitioners in meeting relevant learning outcomes, particular 5.7, by: a) developing guidance and good practice for educational supervisors and other FPH members; and b) identifying placements for PH registrars to work in sustainable development. Who from the SIG is leading on this activity? Jeremy Wight / Jenny Griffiths in consultation with the PH Registrars Sustainable Development network | 1 Guidance (linked to publications above) produced by end March 2018 | Educational supervisors and PH registrars better able to meet and demonstrate learning outcome 5.7. | Informal feedback Survey of members | See above - Guidance: - ES/JW to share a draft policy document with the Core SIG at next meeting following discussion with JW. Next Tuesday. |
|  | 2 Seek expressions of interest from possible organisations for hosting a ‘sustainable development’ placement (e.g. SDU, CSH etc.) by end Oct 2017. 3 Consult with Training Programme Coordinators 4 Publicise to specialty registrars | Database of possible placements established. Database of good practice placements established on Faculty website | Uptake of placements. More Registrars achieving good marks in learning outcomes with regard to sustainable development. | 2. JW explored potential placements in other organisations. Need to understand more about what this will specifically mean and liaising with FPH about what would constitute an approved placement for a registrar. Medact are agreeable in principle Other organisations e.g. The Health Alliance and SDU to be followed up when new Directors are in place. Action: JW HR is following up another potential organisation. Action: HR c/f from earlier meeting DJ exploring potential for Sustainability Fellowships in SD in the Midlands and East region through HEE. – an approach for registrars. Action: DJ to speak to Rachel Stancliffe or Michelle Hanson and to share outcomes with the SIG. |
| - Undertake a stakeholder analysis in order to determine how FPH can best work with other interested organisations in this field, minimising overlap and duplication of effort, and maximising synergy. Who from the SIG is leading on this activity? Jeremy Wight | 1 Identify organisations of interest by end October 2017. 2 Develop framework for determining overlap / underlap / synergy by end October 2017. 3 Complete stakeholder analysis, including communication with relevant organisations if appropriate, by end December 2017. | This will allow prioritisation and alignment of efforts, ensuring that SD SIG has maximum impact given resources available. |  | JB was due to meet Nick Watts (Health Alliance for Climate Change) but he has stood down as Director. David Pencheon has also stood down as Director of the SDU. Action: JB to pick this up in Feb. HR sent notes of FPH SD SIG to GB for information regarding perspectives of 2 Local Authority Health and Wellbeing Board chairs. |

| - Develop a Communications Strategy that includes work with partner organisations, development of the SIG database, and responding /reacting to relevant issues as they emerge. Who from the SIG is leading on this activity? Jeremy Wight / Helen Ross | 1 Review SIG ‘membership’ to distinguish core vs corresponding, areas of interest, etc. by end Sept. | More efficient use of SIG member resources. | - Up to date Database of SIG members including skills and knowledge | JW e mailed information to HR to update database. Thanks to Rachael for providing a way of translating the G mail list. Action: HR to update database by next meeting |
| --- | --- | --- | --- | --- |
|  | 2 Develop communication strategy, building on review of membership and outcome from stakeholder analysis. | More efficient use of resources. Awareness raised within the Faculty of the SIG, how to contact us and what would be of most use to the members. Clear process and route for messages about Climate Change and Sustainable Development and Public Health established within the SIG | - Number of hits on the FPH SIG page from members - Number of press releases issued - Feedback from FPH members considered by SIG and actioned | On hold – waiting for update on FPH website improvements. FPH consulted SIG regarding potential for writing a Blog once or twice a year. The group agreed in principle that this would be a good idea. JJ - Blogs can offer an alternative more informal and chatty form of communication to an article in Public Health Today for example. SH - It would offer a good opportunity to publicise the existence of the SIG, the inspiration behind it and the work that is being developed as a result. Twice a year was thought to be an appropriate frequency. Action: Amanda Donnelly to forward example to HR. Action: HR to report back to JW and JM |
| 5. a) Write a policy discussion paper on an SD and Public Health sustainable development topic (to be agreed) Who from the SIG is leading on this activity? - Amanda Donnelly and Kristin Bash with Jeremy Wight. | 1 Agree topic outline for the series by date… 4 Secure funding by date… 5 Hold the workshop / seminars by date… | The outcomes will inform the FPH on Sustainable Development and Public Health work programme in the future and the next iteration of the FPH competency framework and content | - Report of event - Policy discussion paper presented to FPH Board | 5a) Action: Amanda Donnelly and Kristin Bash working on a paper with JW. Action: JJ to contribute the Good Food East Midlands perspective with AD and KB Draft to be shared with the Core SIG at April meeting for discussion. Action: April Agenda item |
| b) Hold a workshop / seminar to engage and consult with the workforce. Who from the SIG is leading on this activity?Helen Ross – with communications sub group |  |  |  | It was agreed that we would focus our efforts in supporting the 3 day Sustainable Food and Farming conference in Edinburgh in September 2018 as requested by Rob Carlton. Why? The topic is very relevant to SD and public health and could fit well with our workplan. Climate Change and Health, Brexit, Food Security, Action: HR to liaise with FPH over use of logo for conference once draft flier available via AD |

| 6 Hold 4 SIG meetings per year – virtually or in person Who from the SIG is leading on this activity? Jeremy Wight and Helen Ross | 1. FPH Annual conference | 1. engagement with all FPH members | 1. report of SIG meeting at conference |
| --- | --- | --- | --- |
|  | 2 Three other meetings organised per year | 2. engagement with SIG members | 2.report of SIG meetings |
| 7 Present report on progress to the FPH Board Who from the SIG is leading on this activity? Jeremy Wight / Helen Ross | 1. produce draft report | 1. workplan monitored and reported | 1. report against workplan |
|  | 2. circulate for feedback from SIG | 2.Engagement with SIG members | 2. emerging issues identified in report |
|  | 3. Present report to FPH Board | 3. Engagement with FPH Board | 3. FPH Board report and minutes |

4.  Governance

In addition to the activities listed above, all committees must report every quarter on progress against their workplan to the Board, actively support all financial forecasts and budgetary requirements, and produce a final year-end report.  All sub-committees must report to their parent committee who in turn must report to the Board. Each sub-committee will agree how frequently the SIGs should report to them.

5.   Working with other FPH committees and SIGs

|  | Which committees or SIGs have you spoken to in the development of your workplan? | Will you be working with them on any of the activities above? | If so, how? |
| --- | --- | --- | --- |
| 1. | None | Potentially all of them – e.g. Transport SIG | Via e mail, skype, invitations to our meetings. Attendance at the SIG chairs meeting – see HR report. |
| 2. |  |  |  |
| 3. |  |  |  |

6.   Membership engagement and growth

| What are the three main ways your SIG plans to involve FPH members (outside of your own SIG) in the activities listed above? (e.g. consultation exercises, focus groups, surveying, case studies and local examples, encouraging additional members to sit on SIG project groups etc.) | - Through surveys of FPH members and registrars |  |
| --- | --- | --- |
|  | - By gathering good practice case studies from successful registrars and their supervisors (particularly from competency 5.7) |  |
|  | - By continuing to encourage people with expertise from complementary professions to contribute to our understanding and knowledge through open workshops and seminars and meetings |  |
| What are the three things your SIG plans to do to promote its activities to members and the wider public health community? (e.g. blogs, articles in Public Health Today, social media activity, opinion pieces in trade press etc.) | - Two articles in PH Today |  |
|  | - Developing a SD SIG presence on the FPH website |  |
|  | - Holding 2 workshops to inform our publications and guidance |  |
| What are the three main ways you plan to encourage new members to join FPH? | - By providing good guidance for members and registrars about sustainable development and public health |  |
|  | - By promoting our work nationally through attendance / speaker engagement at national and regional conferences and events |  |
|  | 3. Through collaborative working with partner organisations demonstrating FPH commitment to this agenda. |  |
| Approximately how many new members do you think your SIG is likely to encourage to join FPH by December 2018? | Impossible to predict. Our challenge is to actively engage the ones we have. |  |

7.  Income generation

| What are the three main ways you plan to seek to raise income to support your activities and FPH’s wider agenda? | - Application for funding to cover any workshops, publications, as necessary. |
| --- | --- |
|  | 2. |
|  | 3. |
| How much money do you think your SIG will raise? | SIG activities will be determined by the availability of funding, so it is likely that funds raised and expenditure incurred will be equal. |

8.   FPH Conference 2018

Please could you outline how your SIG plans to take part in FPH Conference 2018:

We will present the outcomes of our work at the conference and utilise the opportunity to consult the wider FPH membership about progress and priorities

9.   Resource requirements

FPH recognises the time and energy commitment our members give to the work of SIGs and we want to ensure our support is appropriate.  We currently have very limited staff and financial resources and need to make sure that they are used to greatest effect – whether this is in relation to helping to organise a meeting, paying travel costs or spending time to deliver projects.  Please could you outline how much staff resource or budget you think would be required to deliver your workplan and whether this has been agreed by the relevant FPH director or CEO:

Staff resource – help with administration of the SIG, arranging meetings for the 3 year programme, paying expenses for speakers, help with development of the member database support with policy development and funding bids.

10.  Risk management

Please outline the three main risks associated with this workplan and how you plan to mitigate these risks:

|  | Identified risk | Suggested mitigation |
| --- | --- | --- |
| 1. | Not successful in securing £ | Cut back on work plan. Reduce costs, e.g. by on line publishing only |
| 2. | Non engagement by FPH members due to lack of resources/ time / energy | Make the content relevant to the day job, whilst remaining challenging and realistic about the risks of climate change |

11.   Equality and diversity

Please outline how you have considered the equality and diversity implications for this workplan in accordance with FPH’s E&D policy:

Sustainable Development is a key aspect of equality and diversity. The challenges of climate change and health are clearly identified. We need to meet our climate change targets in order to minimise our climate change impacts on countries that are most susceptible to climate change – often the poorest nations. Link to Stern: http://www.lse.ac.uk/asiaResearchCentre/_files/igPatelLecture_final.pdf

- SIGs overseen by Health Improvement Committee – please return to Jenny Mindell j.mindell@ucl.ac.uk  Chair